## Sheet1
USER CASES : I want to be able to |  | AS A . | SPRINT | PRIORITY | DIFFICULTY
MAKE PARKING WITH ZONES AND SPOTS | ASSIGN ZONES TO PARKING (CHARECTERISTICS) | ADMIN | 1 | HIGH | 2
| ASSIGN AT LEAST 1 SPOT TO ZONE | ADMIN | 1 | HIGH | 2
| DEFINE CHARS OF EACH SPOTS | ADMIN | 1 | HIGH | 2
ASSIGN AND CREATE AT LEAST 1 PRICELIST | DEFINE PRICELIST TIME-PERIOD | ADMIN | 1 | HIGH | 2
| ASSIGN PRICELIST TO ZONE | ADMIN | 2 | HIGH | 3
ASSIGN PRICESCALES TO PRICELIST | DEFINE IF PRICELIST IS SCALING | ADMIN | 2 | HIGH | 3
| DEFINE PRICESCALES IN PRICELIST | ADMIN | 2 | HIGH | 3
CALCULATE COST | CALCULATE COST FROM PRICESCALE | ADMIN | 3 | MEDIUM | 5
| CALCULATE COST FROM PRICELIST | ADMIN | 3 | MEDIUM | 5
SEE HISTORY OF PARKING | STAMP WHEN ENTRY (WHEN ENTRY_TIME IS NOT NULL AND AND EXIT_TIME IN NULL THEN SPOT IS STILL OCCUPIED) | ADMIN | 2 | LOW | 2
SEE CAPACITY | SHOW WHICH SPOTS ARE EMPTY IN EVERY ZONE-PARKING | ADMIN,USER | 2 | MEDIUM | 3
| SHOW THE % OF THE OCCUPATION OF ZONE | ADMIN,USER | 2 | MEDIUM | 3
| SHOW THE % OF THE OCCUPATION OF PARKING | ADMIN,USER | 2 | MEDIUM | 3
CREATE DATABASE | CREATE THE STRUCTURE OF THE DB | DEVELOPER | 1 | HIGH | 2
CREATE API | DEVELOP CLASSES | DEVELOPER | 1 | HIGH | 2
| DEVELOP ENTITIES | DEVELOPER | 1 | HIGH | 2
SEE CURRENT COST | CALCULATE CURRENT COST | ADMIN,USER | 3 | MEDIUM | 5